## Sheet1
Task Number
Task Number | Task Description | Date Due (Planned) When you intend to complete the task | Date Completed (Actual) When you actually completed the task
1 | Create user stories list | 2025-03-14 | 2025-03-15
2 | color scheme + logo + fonts | 2025-03-17 | 2025-03-17
3 | wireframe done + phase 1 | 2025-03-17 | 2025-03-17
4 | create about page | 2025-03-22 | 2025-03-25
5 | create main page | 2025-03-22 | 2025-03-25
6 | create more info + transport page + footer | 2025-03-25 | 2025-03-25
7 | create mailing form with functionality | 2025-03-25 | 2025-03-27
8 | implement all functionality (interactive carousels + google maps) | 2025-03-29 | 2025-03-25
9 | user testing | 2025-03-29 | 2025-03-29
10 | revisions & documentation | 2025-03-31 | 2025-03-29
11
12
13
14
15
...